## Sheet1
CSIS 44-692 Graduate Directed Project II
Spring 2017
SAIKIRAN GANDHAM
Team D - Sigma - Course Scheduling Assistant
Week number | Week beginning (Monday) | Day | Start Time | End Time | Time elapsed | Description of activity
1 | 2017-01-09 | 2017-01-09 | 9:00 | 9:50 | 0:50 | Attend class
|  | 2017-01-09 | 9:50 | 11:00 | 1:10 | Team meeting
|  | 2017-01-09 | 17:00 | 19:00 | 2:00 | Understanding of requirements & project Review
|  | 2017-01-11 | 9:00 | 9:50 | 0:50 | Attend class
|  | 2017-01-11 | 9:50 | 11:00 | 1:10 | Team meeting
|  | 2017-01-11 | 17:00 | 20:00 | 3:00 | Team meeting - Worked on Iteration plan
|  | 2017-01-13 | 9:00 | 9:50 | 0:50 | Attend class
|  | 2017-01-13 | 9:50 | 11:00 | 1:10 | Team meeting
|  | 2017-01-13 | 17:00 | 20:00 | 3:00 | Project Distribution among team members
[5 empty] | 14:00 | WEEKLY TOTAL
2 | 2017-01-16 | 2017-01-16 | 14:00 | 17:00 | 3:00 | Research about back4app connectivity with web application and also about database server and application server.
|  | 2017-01-18 | 9:00 | 9:50 | 0:50 | Attend class
|  | 2017-01-18 | 9:50 | 11:00 | 1:10 | Team meeting
|  | 2017-01-19 | 18:00 | 22:00 | 4:00 | Installed SQL developer, netbeans and developed Entity Relationship model by creating tables
|  | 2017-01-20 | 9:00 | 9:50 | 0:50 | Attend class
|  | 2017-01-20 | 9:50 | 11:00 | 1:10 | Team meeting
|  | 2017-01-20 | 18:00 | 22:00 | 4:00 | Studied about calendar view and how to add drag and drop effects in the view.
[5 empty] | 15:00 | WEEKLY TOTAL
3 | 2017-01-23 | 2017-01-23 | 9:00 | 9:50 | 0:50 | Attend class
|  | 2017-01-23 | 9:50 | 11:00 | 1:10 | Team meeting
|  | 2017-01-23 | 19:20 | 22:40 | 3:20 | Created Database and tables.
|  | 2017-01-25 | 9:00 | 9:50 | 0:50 | Attend class
|  | 2017-01-25 | 9:50 | 11:00 | 1:10 | Team meeting
|  | 2017-01-25 | 20:10 | 22:30 | 2:20 | Worked with Sanket, Nikhil and Harika on Faculty and Admin pages created. Discussed about issues in development phase.
|  | 2017-01-26 | 19:00 | 22:00 | 3:00 | Created a project for Calendar view and resolved issues in drag and drop effects (Worked with Nikhil and Harika)
|  | 2017-01-27 | 9:00 | 9:50 | 0:50 | Attend class
|  | 2017-01-27 | 9:50 | 11:00 | 1:10 | Team meeting
[5 empty] | 14:40 | WEEKLY TOTAL
4 | 2017-01-30 | 2017-01-30 | 9:00 | 9:50 | 0:50 | Attend class
|  | 2017-01-30 | 9:50 | 11:00 | 1:10 | Team meeting
|  | 2017-01-30 | 16:00 | 19:00 | 3:00 | Worked on creating database
|  | 2017-02-01 | 9:00 | 9:50 | 0:50 | Attend class
|  | 2017-02-01 | 9:50 | 11:00 | 1:10 | Team meeting
|  | 2017-02-01 | 17:00 | 19:30 | 2:30 | Worked on calendar view
|  | 2017-02-02 | 16:00 | 18:30 | 2:30 | Integrating calendar view in admin calendar view page
|  | 2017-02-03 | 9:00 | 9:50 | 0:50 | Attend class
|  | 2017-02-03 | 9:50 | 11:00 | 1:10 | Team meeting
|  | 2017-02-03 | 15:00 | 16:00 | 1:00 | Team meeting
[5 empty] | 15:00 | WEEKLY TOTAL
5 | 2017-02-06 | 2017-02-06 | 9:00 | 9:50 | 0:50 | Attend class
|  | 2017-02-06 | 9:50 | 11:00 | 1:10 | Team meeting
|  | 2017-02-06 | 15:00 | 16:00 | 1:00 | Client Meeting
|  | 2017-02-06 | 17:00 | 21:00 | 4:00 | Created java files for database and connected database to the application.
|  | 2017-02-08 | 9:00 | 9:50 | 0:50 | Attend class
|  | 2017-02-08 | 9:50 | 11:00 | 1:10 | Team meeting
|  | 2017-02-09 | 17:00 | 20:00 | 3:00 | Worked on javascript files
|  | 2017-02-10 | 9:00 | 9:50 | 0:50 | Attend class
|  | 2017-02-10 | 9:50 | 11:00 | 1:10 | Team meeting
|  | 2017-02-10 | 15:00 | 16:00 | 1:00 | Team meeting
[5 empty] | 15:00 | WEEKLY TOTAL
6 | 2017-02-13 | 2017-02-13 | 9:00 | 9:50 | 0:50 | Attend class
|  | 2017-02-13 | 9:50 | 11:00 | 1:10 | Team meeting
|  | 2017-02-15 | 9:00 | 9:50 | 0:50 | Attend class
|  | 2017-02-15 | 9:50 | 11:00 | 1:10 | Team meeting
|  | 2017-02-16 | 16:00 | 19:00 | 3:00 | Worked on routing data from database through java script files
|  | 2017-02-16 | 20:00 | 22:00 | 2:00 | Worked on integrating files to the regular project through source tree.
|  | 2017-02-17 | 9:00 | 11:00 | 2:00 | Team meeting
|  | 2017-02-17 | 13:00 | 17:00 | 4:00 | Worked on worklog, mid-sem presentation, project components and etc.
[5 empty] | 15:00 | WEEKLY TOTAL